## Action Items
Person In Charge | Task | Due Date | Status
All | Discuss Organizational Struture | 2014-11-17 | Done
All | Brain Storm | 2014-11-22 | Done
All | Decide on A Time in Early December to Meet with Ted | 2014-11-17
Jenny | Check in With Spec Sheet |  | By Jan.?
Anthony | Check in With Monstaar |  | Done
Jenny | Find a space(s) to Work | CCL | Done
Anthony | Plan Meety with Sunny Allen

## Timeline
Parent Cateogory
| Hardware | [6 empty] | Experiment Design | [8 empty] | Due Date
Beta Version | Temp | Red LED | Humidity | Camera | Pressure | Gas Control (O2, CO2) | Box Structure | Plant Selection | Growth Requirments (Temp) | Growth Requirements (Pressure) | Growth Requirements (humidity) | Growth Requirementes (light) | Growth Requirements (Gas) | How to water plant | What will plant grow in | Nutritional Requirements
Zekun | Controller | Controller | - | - | - | Controller | Design
Zekun | Sensor | Sensor | Sensor | - | Sensor | Sensor | Sensor
Quincy | Code (Quincy) | Code (Jenny) | Code (Quincy) | Code (Justine/ Anthony) | Code | Code | -
Status Notes | Need Mosfet for other peltier cooler. Assess if Humidity can be integrated | http://www.biomedcentral.com/1471-2229/5/17 | Need to buy this: http://www.seeedstudio.com/depot/grove-temphumi-sensor-p-745.html?cPath=144_147 | Grabbed a CMOS OV7670 just to test, but would recommend the camera Pixy camera here (https://www.adafruit.com/product/1906) or the TTL here (http://www.adafruit.com/products/397) for future prototyping |  |  |  | Aradopsis Thaliana?
Fully Functioning / Complete? | [16 empty] | 2015-02-07
Accountable Team member | Anthony | Anthony | Anthony | Anthony | Anthony | Anthony
Target Completion Date | 2014-11-30 | 2014-12-07 | 2014-12-14 | 2014-12-21 | 2014-12-28 | 2014-01-04 | 2014-01-04 | 2014-11-30 | 2014-12-07 | 2014-12-14 | 2014-12-21 | 2014-12-28 | 2014-01-04 | 2014-01-11 | 2014-01-18 | 2014-01-25
Beta Version Final Testing | Wk 1 | Wk2 | Wk3 | Wk4 | Final Wk
Work | Lab bench test | Refine / fix kinks | Lab bench test 2 | Refine / fix kinks | Hail Marry Full of grace
Notes
Target Completion Date | 2014-01-11 | 2014-01-18 | 2014-01-25 | 2014-02-01 | 2014-02-07
| Temp | Full Spectrum Light | Humidity | Camera | Pressure | Gas Control | Box Structure
Improve Phase
Fully Functioning / Complete?
Alignment To Specs

## Light SpecsCalculations
Item | Wave Length | Energy Per Photon | Energy Per uMol | Area of Light | Radiometric Flux (W) | Irradiance (W/m^2) | Number of Photons Per One Watt | Photon Flux (uEinstein)
https://www.berthold.com/en/bio/how-do-i-convert-irradiance-photon-flux | m | Ep = h•(c/λ) | Ep • NA [J] | m^2 |  | E = W/m^2 | [1/(m2•s)] Np | EQF = Np/NA
| given | calculted with constants | Ep * 6.02 * 10^17 | given in specs | given specs (supply with less watts) |  | Np= E/Ep, where E w/m2
http://www.mouser.com/pdfdocs/Luminus_PT54_Specification_PDS1339_Rev07E.pdf | 6.23E-17 | 3.19E-09 | 1.92E+09 | 1.00E-02 | 3 | 3.00E+02 | 9.25E+20 | 1.54E+03
h | 6.63E-34
c | 299800000 |  |  | 0.255
Avogadro's # | 6.022e+23
Np | 1.32E+09
Power (or Energy) | 4.2
Photon Flux | 4.57E+14

## Supply List
Item | Why
MOSFET | cooler
LEd ring
humditiy
O2
CO2
temp

## Model Organisms
Links | Name | Earth Environment | Reproduction | Cost | Pre Seeding | Temp (C) | Time To Germinate (days) | Light | Humidity | Gas | Food | Size in CM (WILL IT FIT IN THE BOX?) | Does someone on our team have experience growing the plant? | Notes
https://abrc.osu.edu/seed-handling | Arabidopsis | dirt | seed | 5-6$ per 250 http://www.arabidopsis.com/main/cat/pricing/!fl.html#pl_tg | yes need to make it cold 4 | 23 | 3 to 5 | red and blue light 120-150 µmol/(m2*sec) | 50% |  |  |  | yes
http://www.jstor.org/discover/10.2307/4539481?uid=3739560&uid=2&uid=4&uid=3739256&sid=21104659508791 | Boechera (sicklepod) | dirt/sand | seed |  |  | 15-30 | 7 | none needed |  | 20% O2 |  | 30 - 90 | no | difficult?
http://onlinelibrary.wiley.com/doi/10.1111/j.1751-1097.1993.tb02967.x/abstract | Selaginella moellendorffii | rocks | spore |  |  | 10 to 24 |  | low light | High |  |  | 15 | no | termed the reserrecution plant because it's hardy and easy to grow
http://brachypodium.pw.usda.gov/files/Bdmodel2009.pdf | Brachypodium distachyon | dirt | seed |  | yes need to make it cold for 4 weeks | 18 to 24 | 28 (requires cold prep) | White light 120-150 µmol/(m2*sec) |  |  |  | 10 to 15 | no
http://www.jove.com/video/50527/methods-for-performing-crosses-setaria-viridis-new-model-system-for | Setaria viridis (foxtail) | [10 empty] | 15 to 115 | no
http://www.victoria-adventure.org/lotus/growing_from_seed.html | Lotus | aquatic | seed |  | May need to sand the seed | 22 to 32 | 7 | [5 empty] | no | seems like a lot of variables to account for
| Lemna | aquatic | seed | [9 empty] | no
http://cornandsoybeandigest.com/seed/seed-science-seed-germination?page=2 | Maize | dirt | seed |  |  | 30 |  |  | 30% |  |  |  | no
http://medicago.org/documents/Protocols/seedgerm.html | Medicago truncatula (legume) |  | seed |  | yes, need to treat them with cold for 36 hours | 25 | 2 to 4 | dark |  |  |  | 10-60 | no
https://ojs.lib.byu.edu/spc/index.php/wnan/article/view/29310 | Mimulus guttatus |  | seed |  |  |  | 3 - 8 |  |  |  |  | 10-80
http://herbalistics.com.au/product_info.php?products_id=764 | Nicotiana benthamiana | sand | seed | 4.40 for 25 | none | 18 to 20 | 7- 21 | 90 μmol/s/m2 | 60 % |  |  | 20 - 150 | no | http://www.plantmethods.com/content/9/1/46
https://www.agronomy.org/publications/aj/abstracts/95/1/184?access=0&view=pdf | Rice | water | seed (well rice) |  |  | 30 to 40 | 3 |  | 100 % |  |  |  |  | Germinated rice is healthier than non germinated rice? http://www.instructables.com/id/HOWTO-make-GBR-germinated-or-sprouted-brown-rice/step1/History-of-GBR/
http://dps.plants.ox.ac.uk/langdalelab/protocols/misc/moss_spores.pdf | moss | dirt | spore |  |  | 25 |  | continous light |  |  |  | yes | no | grows in a spiral in space
http://connection.ebscohost.com/c/articles/79307423/photoinduction-spore-germination-marchantia-polymorpha-l-mediated-by-photosynthesis | Marchantia polymorpha |  | spore |  |  |  |  | red light 10 hours or pulses |  |  |  | 0-10 | no |  | http://pcp.oxfordjournals.org/content/40/10/1014.full.pdf
http://www.plosone.org/article/info%3Adoi%2F10.1371%2Fjournal.pone.0062868 | Populus |  | seed | water | drying for 2 days | 30 | 3 to 7 | dark | 75
Notes on Variables |  | Probably should grow something that works well in hydroponics | The spore vs seed cost is that spores must always be in water | So far not an issue? How many plants will we need to grow to make this project worth while? |  | Should look into temp day and night cycles | How long do we want this experiment to take? | Look into photoblastic plants | Humidity Day and night cycles |  |  | This probably won't matter if we are just trying to prove germination

## Visions of Sugar Plums
Idea | Example | LIST OF PUBLIC ISS EXPERIMENTS
UX interface that can modify parameters of experiment and add different layers of constraints | Control temp w/ in range, then mod to cycle ranges w/ time and or pressure (web based mod of parameters / process) | http://www.nasa.gov/mission_pages/station/research/experiments/experiments_hardware.html
Energy Cell | Contained algae that pulls energy from heat or chemicals.
Programmable Matter
Cure Cancer
Grow a synthetic organism in space | monitor the expression of color changing flowers in space http://revolutionbio.co/
Hackathon: | Developed a proof of concept model with team to show the group coherence is good and we can accomplish our goals.
What we're creating: | A 10cm x 10cm x 10cm bioreactor-containing, experiment specific - automated experimental module
What we plan to do with this: | Refine the concept to be a reasonable cost minature lab for basic science research in any location (desert, ocean, city, space)
Everythign ISS related: | Material selection, data transfer, specs will all have to be up to ISS standards. Really it's just coincidental that we're gogin to ISS.. mainly because it's the only destination in space we know has power outlets. (Step 1: Charage iPhone in space)

## Meeting Times
Name | Time for Team Meeting | TIme For Space Tango Meeting
Jenny | Mon 5-7 pm, Tuesday 5 -7 pm | Tuesday 5-7pm , Wednesday 5-7 pm
Justine | Anytime after 6 on Mon/Tues | After 7 on Tuesday/Wednesday
Anthony | anything but Tuesday or Friday evening | anything but Tuesday or Friday evening
Zekun | Tuesday all day | Tuesday all day, Wednesday 5:30-8
Richard | Monday after 6, Tuesday after 5, Wednesday after 6
Chris | Weekdays after 5pm | weekdays after 5pm
Quincy | MWF after 2pm, TTh after 9pm | MWF after 2pm, TTh after 9pm
Adam | Just about anytime | Just about anytime

## End Goals
Name | Academic, Corporate, or both? | End Vision | What can you contribute? | Recommended Facilitator
Justine | Either one. | Experiments which show how organisms grow and react in space. Also, showing the world how organisms can grow in space, and providing the data online as a way of giving back to the scientific community, so scientists can crunch the data, make inferences, write papers, etc. based on it. Can be corporate, e.g. if we offer to add/activate different modules for a fee (i.e. scientists will only have access to the data from modules that are currently running in the experiment space). | Mostly code for the various modules we have in mind. I can also run front-end dev for our website, and any other interfaces we may need.
Jenny | Either one. | 1. Have fun. 2. Design an experiment and send it to space. I am particularly interested in human vascular systems (cardio valscular, glands, lungs) act in microgravity. I am also interested in growing fuel and food in space. 3. I see biology ending up being something you can CAD. Biology experiments in the future will be able to be modelled online. I think having a small bioreactor to model low cost experiments will needed to validate computational models. 4. Design a consumer product for educational purposes. | enthusiasm, fundraising, bio experiences,
Chris | Corporate but ok with either | Change the world for the better. Develop a research platform that has broad application and can be leveraged across academia, industry, and recreational use. Grow a vision from concept to reality and learn along the way while impacting as many people in a positve way along the journey. | Basic Science research experience; Business development, qualificaiton; operational expertise; manufacturing experience; Leadership, motivation, vision.
Quincy | Academic but slightly okay with Corporate (depending on our goals) | I envision my involvement with this project as mostly growth and learning for me. In the end, I'm willing to help make the project become whatever the consolidated team goal is. I'm willing to adjust to whatever changes happen. Basically, whatever ideas needed to be made reality, I'm going to do my best to make it happen. | TL;DR: hardware, back-end and front-end dev. Basic Electrical Engineering knowledge (soldering, wiring, circuit design, will learn and concentrate on signal processing); Experience with multiple modules for Edison (used them in a different hackathon) (e.g., flex sensors, accelerometers, gyros); Can work with any IDE and programming language depending on available documentation for their API (e.g., Python, C/C++, Javascript); Web Design and Web Data experience (Django, HTML, CSS, Postgres, IoT Analytics).
Adam | Either one, Start out Academic with some open source portions. | Be the premium Bio-research hatch on the International Space Station | CAD, prototypes, Space enthusiasm, manufacturing concepts, miniaturization and packaging experience, PCBA manufacturing, Quality systems to AS9001, ISO9001, MEM's chips, Etch / Deposition chamber experience, Electron and Optical microscope experience, statistics
Anthony | Research / open project seems more likely at first | Make something useful and/or notorious. Learn and have fun. | Control engineering, software, analog and digital hardware.

## Questions for Space Tango
Rank of question importance (1-10 1=low 10=high)
Rank | Jenny | Quincy | Richard | Justine | Zekun | Adam | Chris | Question
10 | 10 | 9 | 10 |  | 10 | 9 | 10 | What is Space Tango looking to get out of this relationship? | A great story.
9 | 10 | 10 | 8 |  | 9 | 6 | 10 | How can Space Tango help us?
9 | 9 |  | 8 |  |  | 9 | 8 | What resources/ experience can we leverage from Space Tango?
8 | 9 |  | 6 |  | 9 | 9 | 7 | Would Space Tango be more keen on working with an academic organizaiton or business? Why?
9 | [5 empty] | 9 | 8 | (All Space tango quesitons but targeted at Magnitude)
8 | 8 |  | 8 |  | 10 |  | 7 | What type of funding could be available and what stage gates would be required to attain more? What would expectations would be set if funding was put in place?
8 | 7 |  | 10 |  | 8 | 5 | 8 | What techincal databases would we gain access to?
9 | 7 |  | 10 |  |  |  |  | What is Magnitude IO's role?
7 |  | 9 | 8 |  | 9 | 3 | 4 | What materials / harware can space tango provide? | Spark Fund
6 |  | 8 | 8 |  | 9 | 3 | 4 | What workspace / tools can space tango provide?
5 | 6 |  | 6 |  |  | 3 | 6 | What SME's would be available to answer questions?
5 | 8 |  | 6 |  | 5 | 2 | 5 | Which of the existing affiliations can we leverage?
7 |  |  | 8 |  |  | 5 |  | Applications are due for space tango at end of Dec, how does that date impact us? | Next Year?
6 | 7 | 3 | 10 |  | 6 | 3 | 5 | What existing affiliations does Space Tango have? | Kentucky Space

## Timeline of Experiments On ISS
Link | Name | Year | Catergory | Worth Trying? | Country | operational requirements | Quick Notes
http://www.nasa.gov/mission_pages/station/research/experiments/528.html | Investigation of a Closed Ecological System (Biosfera) | 2000 | Animal Biology Invertebrates |  | Russia |  | Watch stuff grow in Space
http://www.nasa.gov/mission_pages/station/research/experiments/518.html | Drosophila Motility, Behaviour and Ageing | 2003 | Animal Biology Invertebrates |  |  |  | Fly's age fast in space, there nervous systems don't change much
http://www.nasa.gov/mission_pages/station/research/experiments/154.html | RNA Interference and Protein Phosphorylation in Space Environment Using the NematodeCaenorhabditis elegans (CERISE) | 2009 | Animal Biology Invertebrates |  | Japan |  | Worm muscles in microgravity
http://www.nasa.gov/mission_pages/station/research/experiments/1020.html | Commercial Generic Bioprocessing Apparatus - Synaptogenesis in Microgravity (CGBA-SM) | 2000 | Animal Biology Invertebrates |  | USA |  | Flys in space, temp problems with their box
http://www.nasa.gov/mission_pages/station/research/experiments/199.html | Fungal Pathogenesis, Tumorigenesis, and Effects of Host Immunity in Space (FIT) | 2006 | Animal Biology Invertebrates |  | USA |  | Flys immune systems in space slows down
http://www.nasa.gov/mission_pages/station/research/experiments/1818.html | KS5: Role of Gravity and Geomagnetic Field in Flatworm Regeneration (Flatworm Regeneration) | 2014-15 | Animal Biology Invertebrates |  | USA - Kentucky Space (Ie SpaceTango) |  | Flatworm tissue regeneration
http://www.nasa.gov/mission_pages/station/research/experiments/1116.html | ARC ISS Drosophila Experiment (Fruit Fly Lab-01 (FFL-01)) | 2014 | Animal Biology Invertebrates |  | USA |  | Fly Immune System in Space
http://www.nasa.gov/mission_pages/station/research/experiments/720.html | International Caenorhabditis elegans Experiment First Flight-Aging (ICE-First-Aging) | 2003 | Animal Biology Invertebrates |  | Japan |  | Worms aging in space
http://www.nasa.gov/mission_pages/station/research/experiments/38.html | International Caenorhabditis elegans Experiment First Flight-Cells (ICE-First-Cells) - 10.21.14 | 2003 | Animal Biology Invertebrates |  | Japan |  | Observations suggest that muscles damaged in flight may repair better than muscle damaged on Earth, which runs counter to current thinking. The data also indicate increased muscle protein degradation in the mutant worms, reinforcing the current view that spaceflight-damaged muscles may not properly repair.
http://www.nasa.gov/mission_pages/station/research/experiments/706.html | Cambium (Cambium) | 2009 | Plant Biology |  | USA -Canada |  | Can wood be grown in space? - Information pending- not maghogany
http://www.nasa.gov/mission_pages/station/research/experiments/505.html | Growth Potency of Statoconia (Otoliths) in the Organ of Equilibrium of Gastropod Mollusks in Weightlessness (Statoconia (Otoconium)) | 2004 | Animal Biology Invertebrates |  | Russia |  | Gravity sesors (statoconia) get bigger in microgravity
http://www.nasa.gov/mission_pages/station/research/experiments/1165.html | Antibiotic Effectiveness in Space-1 (AES-1) | 2013 | Microbiology |  | USA |  | Let's grow ecoli in space and treat it with antibiotics and see how this is different than our model preditictions
http://www.nasa.gov/mission_pages/station/research/experiments/1065.html | Advanced Plant EXperiments-02-2 | 2014 | Microbiology |  | USA |  | How do the metabolic pathways of yeast change in space....
http://www.nasa.gov/mission_pages/station/research/experiments/502.html | Optimization of Heterological Expresssion in Yeasts-True Yeasts in Microgravity for Example Synthesis of the HBS Antigen of the Virus Hepatitis B (Antigen (Antigene)) | 2006 | Microbiology |  | Russia |  | Hi, we are Russia and all we will tell the public about a experiment we did 8 years ago was it involved yeast
http://www.nasa.gov/mission_pages/station/research/experiments/449.html | ultivation in Weightless of E.coli- Producer of the Caf1 Protein (Astrovaktsina) | 2007 | Microbiology |  | Russia |  | Hi, we are Russia and all we will tell the public about a experiment we did 8 years ago was it involved yeast
http://www.nasa.gov/mission_pages/station/research/experiments/92.html | Bacterial Acclimation and Adaptation to the Space Environment Conditions-A (BASE-A) | 2006 | Microbiology |  | Belgium |  | Hi we are Belgium and we put bacteria in space
http://www.nasa.gov/mission_pages/station/research/experiments/98.html | Investigation of the Effects of Space Flight Factors on Bacteriophages | 2009 | Microbiology |  | Russia |  | So we, Russia, put bacteriophages in space but we aren't going to the public why
http://www.nasa.gov/mission_pages/station/research/experiments/283.html | Investigation of the Effects of Space Flight Factors on the Technological and Biomedical Characteristics of Bifidobacterium (Bif) | 2009 -2013 | Microbiology |  | Russia |  | Russia and we are mum about microbiology
http://www.nasa.gov/mission_pages/station/research/experiments/498.html | Generation of High Efficiency of Microorganisms for the Production of Preparations of Biodegradable Oil, Organophosphorus Material, Measures for the Protection of Plants, as well as, of Exopolysaddharides Uses in the Petroleum Industry (Bioekologia-M (Bioecology-M)) | 2003-2008 | Microbiology |  | Russia |  | Oil in Space
http://www.nasa.gov/mission_pages/station/research/experiments/499.html | Research and Development of a Self-Contained Reactor of the Shielded Type For Production of Biomass of Microorganisms and Biologically Active Substances (Bioemulsia-Bioreactor-1) | 2004 -2008 | Microbiology | yes | Russia |  | thermal bioreactor
http://www.nasa.gov/mission_pages/station/research/experiments/30.html | Microbial Growth Kinetics Under Conditions of Microgravity (Biokin-4) | 2007-2008 | Microbiology |  | Netherlands
http://www.nasa.gov/mission_pages/station/research/experiments/512.html | Effects of Space Radiation on Food Biocultures (Biokultura (Bioculture)) | 2006 | Microbiology |  | Russia |  | Lets expose food to radition, watch what happens, and not tell the rest of the world - Russia
http://www.nasa.gov/mission_pages/station/research/experiments/202.html | Influence of Factors of the Space Environment on the Condition of the System of Microorganisms-Hosts Relating to the Problem of Environmental Safety of Flight Techniques and Planetary Quarantine (Biorisk-KM) | 2002-2013 | Microbiology |  | Russia |  | The name is the most Russia says about their experiment
http://www.nasa.gov/mission_pages/station/research/experiments/413.html | Influence of the Flow of Heavily Charged Particles of Space Radiation on Gentic Properties of Cell Production | 2006-2013 | Microbiology |  | Russia
http://www.nasa.gov/mission_pages/station/research/experiments/636.html | Growth and Survival of Colored Fungi in Space | 2010-2011 | Microbiology | yes | Romania |  | fungi growth
http://www.nasa.gov/mission_pages/station/research/experiments/52.html | Commercial Generic Bioprocessing Apparatus - Antibiotic Production in Space (CGBA-APS) | 2001-2002 | Microbiology |  | USA
http://www.nasa.gov/mission_pages/station/research/experiments/52.html | DNA Repair in Microgravity: Investigation of the Effects of High Levels of Radiation on DNA Repair Mechanisms in Microgravity (DNARM) | 2006 | Microbiology |  | Russia |  | DNa repair of e coli 375 nm radiation
http://www.nasa.gov/mission_pages/station/research/experiments/900.html | International Space Station High Efficiency Particle Filter Analysis (ISS High Efficiency Particle Filter Analysis) | 2010-2013 | Microbiology | No | USA |  | Craig Venter is sequencing the air in the ISS (go figure)
http://www.nasa.gov/mission_pages/station/research/experiments/1060.html | International Space Station Internal Environments (ISS Internal Environments) | Now? | Microbiology | Yes- the astronauts are in a box, they need to constantly check what's in their box... how do they do it in real time? | All |  | Real-Time - The crew collects and analyzes the sample on ISS. To complete this type of analysis the following tools are used: Compound Specific Combustion Product Analyzer - looks at potential toxic products of combustion, such as a fire, onboard the spacecraft and analyzes carbon monoxide, hydrogen cyanide, hydrogen chloride, and oxygen particles in the air Volatile Organic Analyzer (VOA) - uses gas chromatography/ion mobility spectrometry to isolate volatile compounds in the ISS atmosphere daily Major Constituent Analyzer - monitors the ISS atmosphere continuously for oxygen, nitrogen, carbon dioxide, hydrogen, methane, and water vapor levels. Microbial Air Sampler- U.S. supplied air sampler Ecospherea Kit- Russian supplied air sampler Water Microbiology Kit- U.S. supplied water sampler
http://www.nasa.gov/mission_pages/station/research/experiments/628.html | Investigation of the Processes of Cultivation of Different Types of Cells (Kaskad (Cascade)) | 2009-2013 | Microbiology |  | Russia |  | growing biomass
http://www.nasa.gov/mission_pages/station/research/experiments/457.html | Development of Methods for Designing New Recombinants Producing Strains of Bacteria in Space Flight (Konyugatsia-EFR) | 2003-2008 | Microbiology |  | Russia | thermally controlled container, thermostat
http://www.nasa.gov/mission_pages/station/research/experiments/453.html | Influence of Factors of Space Flight on Lactolen Producer Strains (Lactolen) | 2007-2013 | Microbiology |  | Russia | photo and grow bacteria | Making higher yield of lactolens -aka building blocks http://en.wikipedia.org/wiki/Lactone
http://www.nasa.gov/mission_pages/station/research/experiments/631.html | Microbial Drug Resistance and Virulence (MDRV | 2007-2008 | Microbiology |  | USA
http://www.nasa.gov/mission_pages/station/research/experiments/260.html | POEMS | 2006-2007 | Microbiology |  | USA | grow bacteria | Passively growing bacterai (ie
http://www.nasa.gov/mission_pages/station/research/experiments/494.html | Cultivation of Mesenchymal Stem Cells From Bone Marrow in Space Flight | 2003-2004 | Microbiology |  | Russia |  | info pending
http://www.nasa.gov/mission_pages/station/research/experiments/710.html | Gravitational Effects on Biofilm Formation During Space Flight (Micro-2) | 2010 | Microbiology |  | USA | temp control | biofilms are bad... want to have anti microbial design in space
http://www.nasa.gov/mission_pages/station/research/experiments/882.html | Microbial biofilm formation during space flight (Micro-2A | 2011 | Microbiology |  | USA
http://www.nasa.gov/mission_pages/station/research/experiments/796.html | Genotypic and Phenotypic Changes in Yeast Related to Selective Growth Pressures Unique to Microgravity (Micro-4) - 09.17.14 | 2011 | Microbiology |  | USA |  | yeast in space
http://www.nasa.gov/mission_pages/station/research/experiments/810.html | Investigation of host-pathogen interactions, conserved cellular responses, and countermeasure efficacy during spaceflight using the human surrogate modelCaenorhabditis elegans (Micro-5) | 2014-2015 | Microbiology | Maybe-we would be racing the government | USA |  | lets make worms sick in space
http://www.nasa.gov/mission_pages/station/research/experiments/837.html | Genotypic and Phenotypic Responses of Candida albicans to Spaceflight (Micro-6) - 09.17.14 | 2012-2013 | Microbiology
http://www.nasa.gov/mission_pages/station/research/experiments/893.html | Effect of space environment on mammalian reproduction (Space Pup) | 2013-now | V |  | Japan |  | send freeze dried mouse sperm to space and see the effects
http://www.nasa.gov/mission_pages/station/research/experiments/410.html | Avian Development Facility - Skeletal Development in Embryonic Quail

## Org Structure
Final Roles
Business Development / Experiment setup deisgn specs | Chris
Marketing / Funding / Affiliations | Jenny, Justine
Technology | Anthony
Hardware/ Jenny | Zekun
Software | Quincy
Web | Richard
Software/User interface | Justine,
Quality System | Adam